## Appendix C3 - Pricing Schedule
Appendix C3 - Tenderers Cost Response
Mini-Competition under the Multi Trade Framework for the provision of the internal refurbishment and partial re-construction of the external roof of 13 Hyde Close
Note to Tenderers - Please Complate ALL Yellow Highlighted sections
Tenderer: | <<Your Company Name>>
| Summary | Total | NFDC Comment | Tenderers Comment | Uplift % Rates (as per Multi Trade Tender)
| Contract Sum (£) ExcVAT | 0 |  |  | Uplift Rate %** | Description
[5 empty] | Overhead & Profit Uplift % | This is the uplift % your company would charge on top of the total direct labour costs to cover non-direct labour costs (this is the indirect costs related to management & back office support) and profit margin. | 0%
| Estimated Project Duration (Days) |  |  | Variations - Pricing as per SOR NFDC Multi Trade Framework - Appendix C3 Pricing Response Form | Materials Uplift % | This is the uplift % your company would charge on top of the best value OEM / equivalent material supplier invoice cost e.g. invoice Cost £ + [Y%] uplift charge. | 0%
Note on B4: Tenderers: Please Insert Company Name HERE

## Prelims & General Works
1 | Prelims | Quantity (If Applicable) | Contract Sum (£) Exc. VAT
1.1 | Provision of welfare facilities for duration of works to include Portaloo.
1.2 | Scaffolding – CADE Roofing NFDC appointed framework contractor. To facilitate works within section 3.5 only. | n/a | Management Only. Item 1.7
1.3 | Provision for waste disposal of all waste generated as part of the works detailed in this schedule.
1.4 | Structural Engineer assessment/report of fire damage to roof rafters. | n/a | NFDC
1.5 | Supply of temporary electrical supply to property to enable reinstate works. | n/a | NFDC
1.6 | Building Control Fees, application, plans, required attendances & evidences to be undertaken and provided by contractor.
1.7 | Project management/site supervision as named Principal Contractor under 2015 CDM Regulations. Including liaison and management of NFDC appointed framework subcontractors for specified works detailed later within schedule. To include creation of CPP and collation of H&S file.
| Total Prelims |  | 0

## Removals & Demolitions
2 | Removals/Demolitions | Quantity (If Applicable) | Contract sum (£) Exc VAT
Note: Electrical & Plumbing works in specific schedules.
Property clear of tenants items pictured in Appendix B1, Schedule Appendix B as of December 2024, however contractors to attend site to determine current condition prior to quotation.
2.1 | General
2.1.1 | Allow to clear debris and all loose masonry, timbers, fixtures and fittings from the property as instructed within this schedule. All smoke damaged material must be removed as far as practically possible and treated with the following materials and methods prior to carrying out repairs.
ENCAPUSLANTS: Remove as much of the sooting and charring as far as practically possible, sponge down and wire brush surfaces removing flaking debris and then utilise a suitable encapsulant not a sealer to manage any remaining exposed and underlying materials or contaminants that remain on surfaces. Examples: Exposed Concrete lintels, charred brickwork faces and roof/floor timbers
SEALERS: A water based breathable sealer coat to be applied after all contaminants have been completely removed and surfaces thoroughly cleaned to prevent the reoccurrence of damage such as stains or odours.
Examples: Remaining cleaned plaster surfaces and decorated surfaces as required.
Contractor to notify the contract administrator of the selected products of choice prior to application.
After removals and demolition inform the CA of any joists/rafters that are not scheduled for replacement/reinforcement but are none-the-less damaged with a view for assessment
2.1.2 | Installation of temporary supports as required to allow for removal and then disposal of damaged ceiling/floor joists or other repairs as required.
2.2 | Entrance Hall/Stairway
2.2.1 | Remove and dispose;
Wallpaper
Coving/skirting and architrave
Damaged/damp/delaminated plaster/plasterboard from walls and ceilings
2.2.2 | Remove and dispose of damaged boxing to l/h side of radiator by front door.
2.2.3 | Remove and dispose of front door including frame |  | Included in item 3.7.1
2.2.4 | Remove and dispose of internal door leading to kitchen lobby including frame.
2.3 | Living Room
2.3.1 | Remove and dispose;
Wallpaper
Coving/skirting and architrave
Damaged/damp/delaminated plaster/plasterboard from walls and ceilings (full strip)
Remove damaged window cill.
2.4 | Dining Room
2.4.1 | Remove and dispose;
Wallpaper
Coving/skirting and architrave
Loose/damp/delaminated plaster/plasterboard from walls and ceilings
2.4.2 | Remove and dispose of chipboard subfloor throughout
2.4.3 | Remove and dispose of internal door leading to kitchen lobby including frame.
2.5 | Kitchen Lobby
Note: Kitchen Refurbishment Itemised separately see item 3.3
See plan in Appendix B1, Schedule Appendix A for lobby location
2.5.1 | Remove and dispose;
Skirting and architrave
Loose/damp/delaminated plaster/plasterboard from walls and ceilings
2.5.2 | Allow to remove and dispose of door including frame leading to lean-too. |  | Included in item 3.7.2
2.5.3 | Dispose of shelving units.
2.6 | 1st Floor Hallway
Note: Windows in Window schedule
2.6.1 | Remove and dispose;
Wallpaper
Coving/skirting and architrave
Loose/damp/delaminated plaster/plasterboard from walls and ceilings
2.6.2 | Allow to remove and dispose of timber handrail inclusive of posts and baseplate.
2.6.3 | Remove and dispose of damaged loft hatch | 1no.
2.7 | Bedroom 1
2.7.1 | Remove and dispose;
Wallpaper
Coving/skirting and architrave
Loose/damp/delaminated plaster/plasterboard from walls and ceilings
2.7.2 | Remove and dispose of door and frame
2.7.3 | Allow to remove and dispose of all fire damaged timberwork including floorboards.
2.8 | Bedroom 2
2.8.1 | Remove and dispose;
Wallpaper
Coving/skirting and architrave
Loose/damp/delaminated plaster/plasterboard from walls and ceilings
2.8.2 | Remove and dispose of vent cover by window. | 1no.
2.8.3 | Remove and dispose of door and frame | 1no.
2.9 | Bedroom 3
2.9.1 | Remove and dispose;
Wallpaper
Coving/skirting and architrave
Loose/damp/delaminated plaster/plasterboard from walls and ceilings
2.9.2 | Remove and dispose of timber boxing forming storage cupboard.
2.1 | Bathroom
Note: Bathroom schedule to be priced up as complete works. See Item 3.4
2.1 | Loft (Internal)
2.10.1 | Remove and dispose of fire/smoke damaged insulation throughout.
2.11 | Roofing Works
Note: Roofing schedule priced up as complete works. See Item 3.5
| Total Removals/Demolition |  | 0

## Trade Schedules
3 | Trade Schedules | Quantity (If Applicable) | Contract Sum (£) Exc VAT
3.1 | Electrical Schedule
3.1.1 | Whole house
· Rewire upstairs lighting with 1.5 mm twin and earth, Ashley pendants, crabtree switches
· Rewire ring main 2.5 mm twin and earth, crabtree sockets
Entrance hall/stairwell
· Replace smoke alarm with aico Ei3016 alarm
· Replace switch and pendant after water damage
Livingroom
· Allow to replace sockets and switches after water damage throughout using crabtree or approved similar.
· Replace pendant with Ashley pendant
Dining room
· Check pendant in dining area for correct connection (some cable pushed into ceiling not in ceiling rose), replace pendants with Ashley pendants
· Remove high level TV socket (Tenant alteration)
· Allow to replace sockets and switches after water damage throughout using crabtree or approved similar.
Kitchen – Internal electrics excluding boiler supply form part of kitchen schedule.
Kitchen Lobby
· Remove tenants wiring to out house (installed without permission)
· Allow to replace sockets after water damage throughout using Crabtree or approved similar.
· Replace switch and pendant.
1st Floor Stairwell
· Replace landing pendant with Ashley pendant
· Replace smoke alarm with aico Ei3016 alarm
Bedroom 1
· Rewire sockets using crabtree sockets
· Rewire lighting using Ashley pendants and crabtree switches
· Rewire immersion supply using crabtree 20a dp switch located in airing cupboard
Bedroom 2
· Rewire sockets using crabtree sockets
· Rewire lighting using Ashley pendants and crabtree switches
Bedroom 3
· Rewire sockets using crabtree sockets
· Rewire lighting using Ashley pendants and crabtree switches
Bathroom – Internal electrics to be included in bathroom schedule. Make allowance to run new 10mm supply from consumer unit to electric shower.
3.2 | Plumbing/Heating Schedule
3.2.1 | Loft
· Remove both fire damaged tanks in loft and support structures for tanks
· Install new supports for both tanks
· Install 50 gallon (227 litre) Cold water storage tank to supply cylinder and other sanitary wares that are tank feed
· Install 18 litre feed and expansion tank to feed heating system
· Both mains feed tanks to have isolations on to isolate cold water feeds
· Both tanks to have overflow pipes that meet water regulations
· Pipework in loft to be lagged with 25mm Polyethelene insulation.
Bedroom 1
· Remove all fire damaged pipework
· Install 900 x 400 (36 x 16) indirect vented stainless Cylinder
· Connect Cold water feed from CWST tank in loft with Lever isolation valve
· Connect to existing flow and return pipes under bedroom floor from boiler
· Re pipe flow and return to heating and hot water heating circuit
· Install Grundfos UPS3 pump and pump valves
· Install Drayton Biflo PBBE66S pack
· Install Drayton automatic by pass valve
· Install Adey Magnaclean Professional 2 pack
· Connect heating system to expansion and feed tank with Lever isolation valve on feed
· All electrical wiring for heating system and 5 core supply to boiler to be replaced
· Replace existing radiator with new 600 x 800 K1 radiator with TRV and Lockshield
· Pipework to radiator to be taken back to main flow and return distribution pipework beneath floor.
Bedroom 2
· Remove existing radiator
· Replace with 600 x 800 K1 radiator with TRV and Lockshield
· Pipework to radiator to be taken back to main flow and return distribution pipework beneath floor
Bedroom 3
· Remove existing radiator
· Replace with 600 x 600 K1 radiator with TRV and lockshield
· Pipework to radiator to be taken back to main flow and return distribution pipework beneath floor
Kitchen
· Repair leaking pipe on heating flow
3.2.2 | Kitchen
· Remove push fit fitting and replace with soldered fittings
· Secure with pipe clips heating flow and return 22mm pipework at ceiling level
Secure with pipe clips cold and hot water pipes at ceiling level.
3.2.3 | · Allow to replace radiators in Livingroom and dining room with lockshield and TRVs. Contractor responsible that size and output correct for space heating demand.
3.2.4 | Allow to remove radiators and reinstall in hallway and kitchen lobby to enable plastering works.
3.3 | Kitchen Refurbishment
3.3.1 | OnPoint Building Contractors Ltd. – NFDC Framework Contractor. | 1no. | Management Only. Item 1.7
Removal and disposal of existing kitchen units. Kitchen rewire, new flooring, tiling, plastering and redecoration. (Redecoration and flooring in kitchen Lobby Excluded)
Installation of new kitchen as per Howdens Design Cad Plan No : 25020742466 and OnPoint Quote QU-1113 dated 12th February 2025.
Additional information on specification available on request.
3.4 | Bathroom Refurbishment
3.4.1 | Works specifications as per the NFDC Appendix B2 ‘Bathroom Refurbishments Specification’ Remove and dispose of - shower chair, rails, tiles, toilet, basin, floor covering, shower former, electrical items and ceiling | 1no.
Plasterworks to walls and ceiling to include new boards to ceiling and coving
Supply and install 200mm x 200mm white tiles fixed with waterproof adhesive and grout
Supply and install 1400 x 900 level access tray former with gravity waste
Supply and install Mira Advance Flex
Supply and install 450mm basin and pedestal including lever taps
Supply and install close couple wc and toilet seat
Supply and install non slip floor covering - like for like blue colour (see spec)
Supply and install shower chair
Supply and install 600mm grab rail
Supply and install L rail with curtains
Supply and install 500 x 600 radiator
Supply and install new sealed light
Supply and install new pull cord and light switch
Supply and install boxing to cover pipework
Supply and install window board
3.5 | Roofing Schedule
3.5.1 | Scaffold access for the below to be listed separately as part of prelims listed in section 1.0. |  | Management only. Item 1.7
Specification for roofing works available on request.
Allow to strip tiles (retain to reinstall later),underlay and baton from fire damaged section of rear elevation (North Facing) elevation above Bedroom 1. Allow for minimum of 10m2, note contractor to undertake site survey to ascertain exact quantity.
As per recommendations of the REA structural assessment dated 29th January 2025. Allow to clean smoke damaged timbers and then reinforce damaged roof rafter R3 as per the specification within the report.
Allow to install new underlay and batons and reinstate roof as per specification.
Allow to replace fire damaged soffit and fascia around perimeter of property and replacing with matching goods as best can.
Allow to remove and then supply fire damaged PVC guttering around perimeter of property, include, clips, outlets and downpipes. Flat roof guttering listed below.
As per CADE Roofing (NFDC Framework Contractor) quote dated 19/2/25. available on request
3.5.2 | Cade Roofing. | 8LM | Management only. Item 1.7
Remove and replace guttering from flat roof and replace in White PVC including all required clips, outlets and downpipes. As Per CADE Roofing (NFDC Framework Contractor) quote dated 18/2/25 available on request
3.6 | Structural Works Schedule
3.6.1 | Note: Roof rafter works included in the roofing schedule.
As per recommendations of the REA structural assessment dated 29th January 2025. Allow to clean smoke damaged timbers and then reinforce damaged timber joists J1,J2,J3,J5,J5 as per the specifications within the report.
Allow to check timber floor joists underneath Bedroom 1. If required support joists as per recommendations in REA report, however REA recommend that supports overlap further so that there are a minimum of 2 bolts within the area of overlap at each end. For purposes of the quotation allow to reinforce 1no. floor joists.
3.7 | Door/Window Schedule
3.7.1 | Front Door Composite – White Moorgreen | 1no. | Management only. Item 1.7
Paramount Window and Fascia Ltd. Supply and Install
3.7.2 | Side Door Composite – White Lathkill - Paramount Window and Fascia Ltd. Supply and Install | 1no. | Management only. Item 1.7
3.7.3 | Windows Paramount Window and Fascia Ltd. Supply and Install | 7no. | Management only. Item 1.7
1st Floor Front Bed Left
1st Floor Front Bed Right
1st Floor Bathroom
1st Floor Rear Bedroom Right
1st Floor Toilet
1st Floor Landing 1
1st Floor Landing 2
3.7.4 | Allow to supply and install replacement internal timber doors and frames throughout. Complete with timber architraves.
Door Specification as follows; 35mm internal flush plywood paint grade solid core doors with 19mm Round Bar Latch Door Handles SAA with mortice latch and keep and hang on a pair and a half of 75mm mild steel butt hinges.
| Total Trade Schedules |  | 0

## Reinstatement & Redecorations
4 | Reinstatement and Redecorations | Quantity (If Applicable) | Contract Sum (£) Exc VAT
Note: Paint specification listed in Appendix B1 - section Appendix D2 (pg 100)
Walls and ceilings to receive primer and three coats of emulsion.
4.1 | Entrance Hall/Stairway
4.1.1 | Install plasterboard boxing around service run by front door ready for plastering. Install access panel over stopcock to allow for future access.
Prepare walls for plaster and then plaster reveals, ceilings and walls throughout with a minimum of 5mm skim finishing plaster top coat with British Gypsum Thistle Multi Finish Plaster.
Install new softwood skirting and architrave, install new coving.
Redecorate throughout. Refer to Appendix B1 - section Appendix D2
4.2 | Livingroom
4.2.1 | Board ceiling complete with 9.5mm Gyproc (or equivalent) Plasterboard, tape up and fill in readiness plaster finish. Boards to be fixed and taped breaking joint with 25mm Gyproc (or equivalent) drywall screws at rate in accordance with the manufacturer’s instructions.
Prepare walls for plaster and then plaster reveals, ceilings and walls throughout with a minimum of 5mm skim finishing plaster top coat with British Gypsum Thistle Multi Finish Plaster.
Install new coving and softwood skirting. Supply and install new timber window board.
Redecorate throughout. Refer to Appendix B1 - section Appendix D2
4.3 | Dining Room
4.3.1 | Board ceiling complete with 9.5mm Gyproc (or equivalent) Plasterboard, tape up and fill in readiness plaster finish. Boards to be fixed and taped breaking joint with 25mm Gyproc (or equivalent) drywall screws at rate in accordance with the manufacturer’s instructions.
Prepare walls for plaster and then plaster reveals, ceilings and walls throughout with a minimum of 5mm skim finishing plaster top coat with British Gypsum Thistle Multi Finish Plaster.
Install new coving and softwood skirting.
Supply and install 18mm new moisture resistant T&G chipboard flooring throughout to take new carpet.
Redecorate throughout. Refer to Appendix B1 - section Appendix D2
4.4 | Kitchen Lobby
4.4.1 | Board ceiling complete with 9.5mm Gyproc (or equivalent) Plasterboard, tape up and fill in readiness plaster finish. Boards to be fixed and taped breaking joint with 25mm Gyproc (or equivalent) drywall screws at rate in accordance with the manufacturer’s instructions.
Prepare walls for plaster and then plaster reveals, ceilings and walls throughout with a minimum of 5mm skim finishing plaster top coat with British Gypsum Thistle Multi Finish Plaster.
Install new coving and softwood skirting.
Redecorate throughout. Refer to Appendix B1 - section Appendix D2
4.5 | 1st Floor Hallway
4.5.1 | Board ceiling complete with 9.5mm Gyproc (or equivalent) Plasterboard, tape up and fill in readiness plaster finish. Boards to be fixed and taped breaking joint with 25mm Gyproc (or equivalent) drywall screws at rate in accordance with the manufacturer’s instructions.
Prepare walls for plaster and then plaster reveals, ceilings and walls throughout with a minimum of 5mm skim finishing plaster top coat with British Gypsum Thistle Multi Finish Plaster.
Install new coving and softwood skirting.
Supply and install new timber Bannister/railing complete with baseplate to match existing staircase as best can.
Allow to rubdown and redecorate staircase with gloss as per redecoration specification in Appendix D1.
Allow to supply and install an insulated loft hatch 563x726mm or similar approved.
Redecorate throughout. Refer to Appendix B1 - section Appendix D2
4.6 | Bedroom 1
4.6.1 | Allow to make repairs to window reveal in preparedness to accept new window.
Allow to replace roof plate if required and make good head of window.
Supply and install softwood t&G replacement floorboards at a depth to match existing.
Clean and remove charred materials and wash walls/floors as per general instructions.
Board ceiling complete with 9.5mm Gyproc (or equivalent) Plasterboard, tape up and fill in readiness plaster finish. Boards to be fixed and taped breaking joint with 25mm Gyproc (or equivalent) drywall screws at rate in accordance with the manufacturer’s instructions.
Prepare walls for plaster and then plaster reveals, ceilings and walls throughout with a minimum of 5mm skim finishing plaster top coat with British Gypsum Thistle Multi Finish Plaster.
Install new coving and softwood skirting, supply and install new timber window board.
Redecorate throughout. Refer to Appendix B1 - section Appendix D2
4.7 | Bedroom 2
4.7.1 | Board ceiling complete with 9.5mm Gyproc (or equivalent) Plasterboard, tape up and fill in readiness plaster finish. Boards to be fixed and taped breaking joint with 25mm Gyproc (or equivalent) drywall screws at rate in accordance with the manufacturer’s instructions.
Prepare walls for plaster and then plaster reveals, ceilings and walls throughout with a minimum of 5mm skim finishing plaster top coat with British Gypsum Thistle Multi Finish Plaster.
Install new coving and softwood skirting.
Install new PVC vent cover.
Redecorate throughout. Refer to Appendix B1 - section Appendix D2
4.8 | Bedroom 3
4.8.1 | Board ceiling complete with 9.5mm Gyproc (or equivalent) Plasterboard, tape up and fill in readiness plaster finish. Boards to be fixed and taped breaking joint with 25mm Gyproc (or equivalent) drywall screws at rate in accordance with the manufacturer’s instructions.
Prepare walls for plaster and then plaster reveals, ceilings and walls throughout with a minimum of 5mm skim finishing plaster top coat with British Gypsum Thistle Multi Finish Plaster.
Install new coving and softwood skirting.
Form new storage cupboard in location of previously removed. Allow for as near like for like replacement including timber door complete with ironmongery and internal clothes rail.
Redecorate throughout. Refer to Appendix B1 - section Appendix D2
4.9 | Loft (Internal)
4.9.1 | Ensure loft area is clean and clear of debris then supply and install rolled loft insulation to a depth of 270mm throughout. Ensure all areas required for proper ventilation of the roof space (such as ventilated soffits) are free from blockage.
| Total - Reinstatement and redecorations |  | 0

## Finishes
5 | Finishes | Quantity (If Applicable) | Contract Sum (£) Exc VAT
5.1 | Allow to supply and install replacement carpet to dining room, stairway and all of 1st floor excluding the bathroom, to include underlay gripper rods and threshold strips.
Carpet to be grey low pile, Corfe Twist 196 (Carpet Barn) or similar agreed.
5.2 | Allow to clean site prior to handover.
| Total - Finishes |  | 0