## Sheet1
Job Number (Order) | Duration standard (Visit) | Duration | Name (Address) | Postcode (Order) | Appointment reason (Visit) | Template name (Visit) | Order comment (Order) | Appointment Date
D017653 | 240 |  | 4A The Weal, Bath, BA1 4EX | BA1 4EX |  |  | 2 4"x4" fence posts, 1 600mm gate and a 6"x6" fence panel needed. | 2025-08-11
D037607 | 360 |  | 14 Padfield Close, Bath, BA2 1NA | BA2 1NA | FIRST | CARPENTER3 | 1 carp 6 hours to install a weather strip on threshold of front door. To install an internal door 6ft x 2.6ft grained 6 panel on the downstairs washroom and replace the mortice lock on the upstairs bathroom | 2025-08-26
D037594 | 240 |  | 14 Padfield Close, Bath, BA2 1NA | BA2 1NA |  |  | tenant can only do a PM appointment to inspect and repair french patio doors | 26/08/2025
D012379 | 360 |  | 22 Dairy Way, Chew Stoke, Bristol, BS40 8UP | BS40 8UP | SECOND | CARPENTER2 | 1 op 4 hours to replace garden gate gate size is 1100w x 1700l / External Fencing and Gates Repair Gate | 01/08/2025
C985918 | 480 |  | 39 Withies Way, Midsomer Norton, Radstock, BA3 2NE | BA3 2NE | FOLLOW ON | CARPENTER3 | Julian withey on overtime to build a lockable case for the consumer unit as child keeps flicking all the switches | 20/08/2025
D045172 | 480 |  | 5 Weal Terrace, The Weal Weston, Bath, BA1 4ET | BA1 4ET | FIRST | CARPENTER32PERSONS | 2 ops all day too fit 6 rolls of 150m of loft insulation going both ways conforming with regs. remove boarding at loft hatch to allow insulation about | 2025-08-28
C853430 | 480 |  | Block 1-4, Dairy Way, Chew Stoke, Bristol, BS40 8UP | BS40 8UP | MANAGER REQUEST | 2MAN_CARP3_GEN3 | Lock to Dave and Kev all day to fit key clamp handrails on the communal steps, / External Building and Groundworks Path Repair/ Concrete or Slabs m2 | No Date - complete ASAP
C714645 | 480 |  | Block 5-8, Rosslyn Close, Bath, BA1 3JU | BA1 3JU | ACCOMODATE PRIORITY JOB | GENERAL32Persons | Kev W and 1 other trade - 1 day - tower scaffold to look at both down pipes by no 2-3 and 5-6 / External Roof Gutters Downpipes Chimney Gutters | 2025-08-14
C821182 | 270 |  | Block 64 66, Laxton Way, Peasedown St John, Bath, BA2 8TA | BA2 8TA |  |  | 2 ops to return to clear back garden of gutters and replace 2 running out lets on the front and back WHITE SQUARE PLASTIC GUTTERS | 2025-09-05
D046738 | 480 |  | 12 Somer Close, Midsomer Norton, Radstock, BA3 2QG | BA3 2QG |  |  | To cut back 4 inches from slab to fit 2.5 length of aco channel to feed into drain by back door. To also fit 6 bags of south cerney shingle and sheet or turam, roughly 1.5sqm to create french drain at rear of property. | 2025-09-09
D046759 | 480 |  | 12 Somer Close, Midsomer Norton, Radstock, BA3 2QG | BA3 2QG |  |  | Push back the insulation into the eaves at front and back. Adjust insulation accordingly throughout loft where there are bare patches and fit lat vents throughout | 2025-08-22
D006689 | 480 |  | 21 Padfield Close, Bath, BA2 1NA | BA2 1NA |  |  | 2 ops 8 hours to relay front path pick up 2 900x600 slabs prior to job and take 12 bags of sand and 3 bags of cement slab lifter required | 2025-08-18