## Sage Homes - WIP Report
Job No | Title | Type | Status | Issue Date | Days Outstanding | Deadline | Target Days | End Date | Days To Complete | Invoice Date | Days To Invoice | Date Booked | Days To Book | Appointment Count | First Appointment Date | First Date Attended | Recall Count | Complaint Count
66429 | Customer reporting a leak from his property through the ceiling | Emergency repair | Complete | 2024-10-16 |  | 2024-10-17 | 1 | 2024-10-17 | 1 | 2024-11-08 | 22 | 2024-10-16 | 0 | 1 | 2024-10-17 | 2024-10-17 | 0 | 0
66390 | Customer reporting a leak coming through the ceiling | Emergency repair | Complete | 2024-10-15 |  | 2024-10-16 | 1 | 2024-12-10 | 56 | 2024-12-19 | 9 | 2024-10-15 | 0 | 4 | 2024-10-16 | 2024-10-16 | 0 | 0
66333 | Letter box for Apartment 1! - Please attend to repair | Routine repair | Complete | 2024-10-11 |  | 2024-10-31 | 20 | 2024-10-24 | 13 | 2024-11-19 | 26 | 2024-10-14 | 3 | 1 | 2024-10-24 | 2024-10-24 | 0 | 0
66175 | Push down button on the toilet is not working - | Routine repair | Complete | 2024-10-02 |  | 2024-10-22 | 20 | 2024-10-10 | 8 | 2024-11-07 | 28 | 2024-10-07 | 5 | 1 | 2024-10-10 | 2024-10-10 | 0 | 0
66172 | Please attend for the communal garden gate that has snapped | Routine repair | Complete | 2024-10-02 |  | 2024-10-22 | 20 | 2024-10-04 | 2 | 2024-11-19 | 46 | 2024-10-02 | 0 | 1 | 2024-10-04 | 2024-10-04 | 0 | 0
66046 | Customer reporting that there is plaster coming away from the | Routine repair | Complete | 2024-09-24 |  | 2024-10-14 | 20 | 2024-10-24 | 30 | 2024-11-19 | 26 | 2024-09-25 | 1 | 2 | 2024-10-08 | 2024-10-08 | 0 | 0
66016 | Back door lock is stiff - please attend to resolve | Routine repair | Complete | 2024-09-23 |  | 2024-10-13 | 20 | 2024-10-02 | 9 | 2024-11-08 | 37 | 2024-09-30 | 7 | 1 | 2024-10-02 |  | 0 | 0
66014 | Paving outside front door is damaged and required replacing - | Routine repair | Complete | 2024-09-23 |  | 2024-10-13 | 20 | 2024-09-26 | 3 | 2024-11-08 | 43 | 2024-09-25 | 2 | 1 | 2024-09-26 | 2024-09-26 | 0 | 0
66003 | Please attend on first visit toilet is on constant flush | Routine repair | Complete | 2024-09-22 |  | 2024-10-10 | 20 | 2024-09-22 |  | 2024-11-08 | 47 |  |  | 0 |  | 2024-09-24 | 0 | 0
65979 | Please attend to replace the light bulb or light fitting | Routine repair | Complete | 2024-09-19 |  | 2024-10-09 | 20 | 2024-09-23 | 4 | 2024-11-08 | 46 | 2024-09-19 | 0 | 1 | 2024-09-23 | 2024-09-23 | 0 | 0
65962 | Carbon Monoxide alarm is beeping three times every few minutes | Emergency repair | Complete | 2024-09-19 |  | 2024-09-20 | 1 | 2024-09-20 | 1 | 2024-11-08 | 49 | 2024-09-19 | 0 | 1 | 2024-09-20 | 2024-09-20 | 0 | 0
65903 | relay insulation and extractor fan | Routine repair | Complete | 2024-09-13 |  | 2024-10-03 | 20 | 2024-09-25 | 12 | 2024-11-08 | 44 | 2024-09-17 | 4 | 1 | 2024-09-25 | 2024-09-25 | 0 | 0
65902 | KEY CUSTOMER- PLEASE ENSURE ALL WORKS ARE COMPLETED ANY QUESTIONS | Routine repair | Complete | 2024-09-13 |  | 2024-10-03 | 20 | 2024-10-23 | 40 | 2024-11-08 | 16 | 2024-09-17 | 4 | 4 | 2024-09-25 | 2024-09-25 | 0 | 0
65901 | Mixer valve for the shower is not working | Routine repair | Complete | 2024-09-13 |  | 2024-10-03 | 20 | 2024-09-24 | 11 | 2024-11-08 | 45 | 2024-09-19 | 6 | 1 | 2024-09-24 | 2024-09-24 | 0 | 0
65859 | Tenant is calling to advise that her kitchen/lounge window is | Routine repair | Complete | 2024-09-12 |  | 2024-10-02 | 20 | 2024-09-18 | 6 | 2024-11-08 | 51 | 2024-09-13 | 1 | 1 | 2024-09-18 | 2024-09-18 | 0 | 0
65843 | Please attend to mould spots around the flat | Routine repair | Complete | 2024-09-11 |  | 2024-10-01 | 20 | 2024-09-23 | 12 | 2024-11-08 | 46 | 2024-09-12 | 1 | 1 | 2024-09-23 | 2024-09-23 | 0 | 0
65807 | Q1: What is the problem? Roof leaking Q2: Where is | Routine repair | Quote sent | 2024-09-09 | 314 | 2024-09-29 | 20 | 2024-10-08 |  |  |  | 2024-09-09 | 0 | 2 | 2024-09-18 | 2024-09-16 | 0 | 0
65799 | Water leak coming from the roof - please attend to | Routine repair | Complete | 2024-09-06 |  | 2024-09-26 | 20 | 2024-10-10 | 34 | 2024-11-08 | 29 | 2024-09-11 | 5 | 2 | 2024-09-16 | 2024-10-10 | 0 | 0
65754 | PLEASE PROVIDE NOTICE NO SAME DAY APPOINTMENTS UNLESS VERBALLY AGREED | Routine repair | Complete | 2024-09-04 |  | 2024-09-24 | 20 | 2024-09-06 | 2 | 2024-09-20 | 14 | 2024-09-06 | 2 | 1 | 2024-09-06 | 2024-09-06 | 0 | 0
64939 | Please attend for the back patio door thats not fitting | Emergency repair | Complete | 2024-08-08 |  | 2024-08-09 | 1 | 2024-08-09 | 1 | 2024-09-20 | 42 | 2024-08-08 | 0 | 1 | 2024-08-09 | 2024-08-09 | 0 | 0
64936 | please attend for broken flush on the toilet and bath | Routine repair | Complete | 2024-08-08 |  | 2024-08-28 | 20 | 2024-09-11 | 34 | 2024-11-08 | 58 | 2024-09-03 | 26 | 2 | 2024-08-23 | 2024-08-23 | 0 | 0
64901 | Cracks around the front door frame | Routine repair | Complete | 2024-08-06 |  | 2024-08-26 | 20 | 2024-08-21 | 15 | 2024-09-20 | 30 | 2024-08-11 | 5 | 1 | 2024-08-21 |  | 0 | 0
64900 | When tenant flushes the toilet | Routine repair | Complete | 2024-08-06 |  | 2024-08-26 | 20 | 2024-08-21 | 15 | 2024-09-20 | 30 | 2024-08-12 | 6 | 1 | 2024-08-21 | 2024-08-21 | 0 | 0
64873 | The Lounge window handle has completely sheared off and the | Routine repair | Complete | 2024-08-06 |  | 2024-08-26 | 20 | 2024-08-21 | 15 | 2024-09-20 | 30 | 2024-08-11 | 5 | 1 | 2024-08-21 | 2024-08-21 | 0 | 0
64850 | Cistern leaking - please attend to resolve | Routine repair | Complete | 2024-08-02 |  | 2024-08-22 | 20 | 2024-08-27 | 25 | 2024-09-20 | 24 | 2024-08-09 | 7 | 1 | 2024-08-27 | 2024-08-27 | 0 | 0
64819 | 2nd Quote required - There is damp appearing in all | Routine repair | Quote sent | 2024-07-30 | 355 | 2024-08-19 | 20 | 2024-08-21 |  |  |  | 2024-08-08 | 9 | 1 | 2024-08-21 | 2024-08-21 | 0 | 0
64800 | Please attend to inspect both of the smoke alarm in | Emergency repair | Complete | 2024-07-29 |  | 2024-07-30 | 1 | 2024-07-31 | 2 | 2024-09-20 | 51 | 2024-07-29 | 0 | 2 | 2024-07-29 |  | 0 | 0
64783 | containable leak to cistern- customer no specified room | Routine repair | Complete | 2024-07-26 |  | 2024-08-15 | 20 | 2024-08-14 | 19 | 2024-09-20 | 37 | 2024-07-30 | 4 | 1 | 2024-08-14 | 2024-08-14 | 0 | 0
64782 | following on from PO00010015 - Glazing:Extra cost for provide and | Routine repair | Complete | 2024-07-26 |  | 2024-08-15 | 20 | 2024-09-16 | 52 | 2024-09-20 | 4 | 2024-09-11 | 47 | 1 | 2024-09-16 | 2024-09-16 | 0 | 0
64773 | Customer having issues with the shower and bath tap not | Routine repair | Complete | 2024-07-26 |  | 2024-08-15 | 20 | 2024-07-31 | 5 | 2024-09-20 | 51 | 2024-07-30 | 4 | 1 | 2024-07-31 | 2024-07-31 | 0 | 0
64724 | As discussed with Dana -BOOK FOR WEDNESDAY 31ST JULY CALL | Routine repair | Complete | 2024-07-25 |  | 2024-08-14 | 20 | 2024-07-31 | 6 | 2024-09-20 | 51 | 2024-07-28 | 3 | 1 | 2024-07-31 | 2024-07-31 | 0 | 0
64577 | Leak under kitchen sink - trace/trace and resolve | Routine repair | Complete | 2024-07-22 |  | 2024-08-11 | 20 | 2024-08-29 | 38 | 2024-09-20 | 22 | 2024-07-30 | 8 | 1 | 2024-08-29 |  | 0 | 0
64575 | Our surveyor will meet Phillip on Monday 22nd July at | Routine repair | Quote sent | 2024-07-22 | 363 | 2024-08-11 | 20 | 2024-07-22 | [5 empty] | 0 |  |  | 0 | 0
64440 | *Mould has been reported by tenant and not yet inspected | Routine repair | Complete | 2024-07-18 |  | 2024-08-07 | 20 | 2024-08-07 | 20 | 2024-08-12 | 5 | 2024-07-18 | 0 | 1 | 2024-08-07 | 2024-08-07 | 0 | 0
64439 | Bathroom light switch is not working - please attend to | Routine repair | Complete | 2024-07-18 |  | 2024-08-07 | 20 | 2024-08-07 | 20 | 2024-09-20 | 44 | 2024-07-18 | 0 | 1 | 2024-08-07 |  | 0 | 0
64435 | Pipe leaking in the bathroom - please attend to resolve | Routine repair | Complete | 2024-07-18 |  | 2024-08-07 | 20 | 2024-09-16 | 60 | 2024-09-20 | 4 | 2024-07-18 | 0 | 2 | 2024-07-23 | 2024-07-23 | 0 | 0
64434 | Gap between window and frame - bedroom window | Routine repair | Complete | 2024-07-18 |  | 2024-08-07 | 20 | 2024-09-16 | 60 | 2024-09-20 | 4 | 2024-07-18 | 0 | 2 | 2024-07-23 | 2024-07-23 | 0 | 0
64408 | *Mould has been reported by tenant and not yet inspected | Routine repair | Complete | 2024-07-16 |  | 2024-08-05 | 20 | 2024-09-18 | 64 | 2024-09-20 | 2 | 2024-07-16 | 0 | 3 | 2024-07-24 | 2024-07-24 | 0 | 0
64357 | Back patio double door - This whole frame is faulty | Routine repair | Complete | 2024-07-11 |  | 2024-07-31 | 20 | 2024-07-19 | 8 | 2024-09-20 | 63 | 2024-07-12 | 1 | 1 | 2024-07-19 | 2024-07-19 | 0 | 0
64303 | Sink tap is broken - please advise if caused by | Routine repair | Complete | 2024-07-05 |  | 2024-07-25 | 20 | 2024-07-17 | 12 | 2024-09-20 | 65 | 2024-07-09 | 4 | 2 | 2024-07-10 | 2024-07-17 | 0 | 0
64302 | Please attend and check soil stack clear to the entire | Routine repair | Complete | 2024-07-05 |  | 2024-07-25 | 20 | 2024-07-08 | 3 | 2024-09-20 | 74 | 2024-07-05 | 0 | 1 | 2024-07-08 | 2024-07-09 | 0 | 0
64243 | The main doors care hard to open from inside and | Routine repair | Complete | 2024-07-03 |  | 2024-07-23 | 20 | 2024-07-05 | 2 | 2024-08-12 | 38 | 2024-07-03 | 0 | 1 | 2024-07-05 | 2024-07-05 | 0 | 0
64223 | ecommend that a full damp | Routine repair | Complete | 2024-07-01 |  | 2024-07-21 | 20 | 2024-07-09 | 8 | 2024-09-20 | 73 | 2024-07-02 | 1 | 1 | 2024-07-09 |  | 0 | 0
64117 | Water leaking from under the sink - please attend to | Emergency repair | Complete | 2024-06-24 |  | 2024-06-25 | 1 | 2024-06-25 | 1 | 2024-08-12 | 48 | 2024-06-24 | 0 | 1 | 2024-06-25 | 2024-06-25 | 0 | 0
63558 | Please for gutter at the front that are overflowing | Routine repair | Complete | 2024-06-14 |  | 2024-07-04 | 20 | 2024-06-21 | 7 | 2024-08-12 | 52 | 2024-06-17 | 3 | 1 | 2024-06-21 | 2024-06-21 | 0 | 0
63557 | Please attend for something to check the oven thats tripping | Routine repair | Complete | 2024-06-14 |  | 2024-07-04 | 20 | 2024-06-27 | 13 | 2024-07-04 | 7 | 2024-06-14 | 0 | 2 | 2024-06-19 | 2024-06-18 | 0 | 0
63516 | Please attend for rear door not closing on its own | Routine repair | Complete | 2024-06-13 |  | 2024-07-03 | 20 | 2024-06-17 | 4 | 2024-06-20 | 3 | 2024-06-13 | 0 | 1 | 2024-06-17 | 2024-06-17 | 0 | 0
63423 | Cistern leaking/running constantly - please attend to repair If follow | Routine repair | Complete | 2024-06-07 |  | 2024-06-27 | 20 | 2024-06-19 | 12 | 2024-06-20 | 1 | 2024-06-13 | 6 | 1 | 2024-06-19 |  | 0 | 0
63417 | The flush seems to be faulty | Routine repair | Complete | 2024-06-07 |  | 2024-06-27 | 20 | 2024-06-17 | 10 | 2024-07-04 | 17 | 2024-06-11 | 4 | 1 | 2024-06-17 | 2024-06-17 | 0 | 0
63408 | Tenant has advised there is a hole/holes in the roof | Routine repair | Complete | 2024-06-07 |  | 2024-06-27 | 20 | 2024-06-18 | 11 | 2024-08-12 | 55 | 2024-06-11 | 4 | 1 | 2024-06-18 | 2024-06-18 | 0 | 0
63404 | Bin store doors don’t lock correctly door needs adjusting- noted | Routine repair | Complete | 2024-06-07 |  | 2024-06-27 | 20 | 2024-06-10 | 3 | 2024-07-18 | 38 | 2024-06-10 | 3 | 1 | 2024-06-10 | 2024-06-10 | 0 | 0
63399 | tenant has called up with regards to some repairs | Routine repair | Complete | 2024-06-07 |  | 2024-06-27 | 20 | 2024-06-18 | 11 | 2024-07-18 | 30 | 2024-06-11 | 4 | 1 | 2024-06-18 | 2024-06-18 | 0 | 0
63374 | The leak is coming from the bath room to the | Routine repair | Complete | 2024-06-06 |  | 2024-06-26 | 20 | 2024-06-12 | 6 | 2024-07-18 | 36 | 2024-06-07 | 1 | 1 | 2024-06-12 | 2024-06-12 | 0 | 0
63371 | Extractor fan in the bathroom removed following on from a | Routine repair | Complete | 2024-06-06 |  | 2024-06-26 | 20 | 2024-06-11 | 5 | 2024-07-18 | 37 | 2024-06-06 | 0 | 1 | 2024-06-11 | 2024-06-11 | 0 | 0
63308 | Please attend to unlock front door as the tenant cannot | Emergency repair | Complete | 2024-06-05 |  | 2024-06-06 | 1 | 2024-09-11 | 98 | 2024-11-07 | 57 | 2024-06-07 | 2 | 2 | 2024-06-07 | 2024-06-07 | 0 | 0
63145 | Customer advises the french doors are draughty | Routine repair | Complete | 2024-05-28 |  | 2024-06-17 | 20 | 2024-06-07 | 10 | 2024-06-27 | 20 | 2024-06-07 | 10 | 1 | 2024-06-07 | 2024-06-17 | 0 | 0
62580 | Sale void works : Hallway- Smoke alarm removed - alarm | Major void | Complete | 2024-05-20 |  | 2024-06-09 | 20 | 2024-06-11 | 22 | 2024-07-18 | 37 | 2024-05-20 | 0 | 1 | 2024-06-11 | 2024-06-11 | 0 | 0
62572 | Sale-void works -Rust starting on hob -Gas meter door not | Major void | Complete | 2024-05-20 |  | 2024-06-09 | 20 | 2024-10-08 | 141 | 2024-11-07 | 30 | 2024-05-20 | 0 | 2 | 2024-05-22 | 2024-05-23 | 0 | 0
62523 | There is no water flow to the outside garden tap | Routine repair | Complete | 2024-05-16 |  | 2024-06-05 | 20 | 2024-05-23 | 7 | 2024-05-24 | 1 | 2024-05-20 | 4 | 2 | 2024-05-23 | 2024-05-23 | 0 | 0
62519 | Please attend to resolve issues with temperature issues - shower | Routine repair | Complete | 2024-05-16 |  | 2024-06-05 | 20 | 2024-07-08 | 53 | 2024-07-18 | 10 | 2024-05-20 | 4 | 2 | 2024-05-29 | 2024-05-29 | 0 | 0
62509 | The shower head holder and bar that is meant to | Routine repair | Complete | 2024-05-16 |  | 2024-06-05 | 20 | 2024-05-16 | 0 | 2024-07-18 | 63 | 2024-05-16 | 0 | 1 | 2024-05-16 | 2024-05-16 | 0 | 0
62411 | Please attend to resolve issues with leaking shower hose | Routine repair | Complete | 2024-05-13 |  | 2024-06-02 | 20 | 2024-06-12 | 30 | 2024-07-18 | 36 | 2024-05-13 | 0 | 2 | 2024-05-17 | 2024-05-17 | 0 | 0
62406 | Leak under kitchen cupboard | Routine repair | Complete | 2024-05-13 |  | 2024-06-02 | 20 | 2024-06-10 | 28 | 2024-09-09 | 91 | 2024-05-13 | 0 | 2 | 2024-05-29 | 2024-05-17 | 0 | 0
62391 | Please attend for the following: Q2 = What is the | Routine repair | Complete | 2024-05-10 |  | 2024-05-30 | 20 | 2024-09-11 | 124 | 2024-09-20 | 9 | 2024-05-13 | 3 | 5 | 2024-05-17 | 2024-05-20 | 0 | 0
62296 | Pre-sale VOID works: - Cracks on staircase joins -Damp patch | Major void | Complete | 2024-05-07 |  | 2024-05-27 | 20 | 2024-06-10 | 34 | 2024-07-18 | 38 | 2024-05-21 | 14 | 2 | 2024-05-22 | 2024-05-22 | 0 | 0
62295 | Pre-sale VOID works: Back door very hard to open | Major void | Complete | 2024-05-07 |  | 2024-05-27 | 20 | 2024-05-22 | 15 | 2024-05-24 | 2 | 2024-05-21 | 14 | 1 | 2024-05-22 | 2024-05-22 | 0 | 0
62239 | Please attend for a roof leak that is coming through | Routine repair | Complete | 2024-05-02 |  | 2024-05-22 | 20 | 2024-05-13 | 11 | 2024-05-21 | 8 | 2024-05-10 | 8 | 1 | 2024-05-13 | 2024-05-14 | 0 | 0
62238 | Please attend for the smoke alarms that are running on | Routine repair | Complete | 2024-05-02 |  | 2024-05-22 | 20 | 2024-05-14 | 12 | 2024-05-15 | 1 | 2024-05-10 | 8 | 1 | 2024-05-14 | 2024-05-14 | 0 | 0
62212 | Pre-sale VOID works: Bed 2 - Door not flush Kitchen | Major void | Complete | 2024-05-01 |  | 2024-05-21 | 20 | 2024-06-11 | 41 | 2024-08-08 | 58 | 2024-06-06 | 36 | 1 | 2024-06-11 | 2024-06-11 | 0 | 0
62164 | Please attend to resolve issues with leaky cistern | Routine repair | Complete | 2024-04-29 |  | 2024-05-19 | 20 | 2024-05-02 | 3 | 2024-05-08 | 6 | 2024-09-03 | 127 | 1 | 2024-05-02 | 2024-05-02 | 0 | 0
62100 | Please attend for customers door handle on her front door | Routine repair | Complete | 2024-04-29 |  | 2024-05-19 | 20 | 2024-06-12 | 44 | 2024-07-18 | 36 | 2024-06-06 | 38 | 1 | 2024-06-12 | 2024-05-01 | 0 | 0
62089 | Urgent - Please attend to check the communal back door | Routine repair | Complete | 2024-04-26 |  | 2024-05-16 | 20 | 2024-05-02 | 6 | 2024-05-15 | 13 | 2024-09-03 | 130 | 1 | 2024-05-02 | 2024-05-02 | 0 | 0
62072 | Please attend to resolve issues with loose tap | Routine repair | Complete | 2024-04-26 |  | 2024-05-16 | 20 | 2024-05-01 | 5 | 2024-05-15 | 14 | 2024-09-03 | 130 | 1 | 2024-05-01 | 2024-05-01 | 0 | 0
62065 | Sale VOID works: -fallen fence -The Meter cupboard key opener | Major void | Complete | 2024-04-25 |  | 2024-05-15 | 20 | 2024-06-13 | 49 | 2024-07-18 | 35 | 2024-06-12 | 48 | 1 | 2024-06-13 | 2024-06-13 | 0 | 0
61707 | Please attend for blocked downstairs toilet and leaking kitchen sink | Routine repair | Complete | 2024-04-19 |  | 2024-05-09 | 20 | 2024-04-22 | 3 | 2024-05-09 | 17 | 2024-04-22 | 3 | 1 | 2024-04-22 | 2024-04-22 | 0 | 0
61561 | Extractor fan in the kitchen is not working - please | Routine repair | Complete | 2024-04-15 |  | 2024-05-05 | 20 | 2024-04-23 | 8 | 2024-05-07 | 14 | 2024-04-15 | 0 | 1 | 2024-04-23 | 2024-04-23 | 0 | 0
61554 | Urgently Please attend to change kitchen battern light | Routine repair | Complete | 2024-04-15 |  | 2024-05-05 | 20 | 2024-04-16 | 1 | 2024-05-09 | 23 | 2024-04-15 | 0 | 1 | 2024-04-16 | 2024-04-16 | 0 | 0
61508 | Urgent- Customer advised that the window on the front door | Emergency repair | Complete | 2024-04-11 |  | 2024-04-12 | 1 | 2024-06-07 | 57 | 2024-07-29 | 52 | 2024-04-15 | 4 | 3 | 2024-04-15 | 2024-04-15 | 0 | 0
61438 | Please attend to check the kitchen florescent light that is | Routine repair | Complete | 2024-04-09 |  | 2024-04-29 | 20 | 2024-04-11 | 2 | 2024-05-24 | 43 | 2024-09-03 | 147 | 1 | 2024-04-11 | 2024-04-11 | 0 | 0
61193 | Mould has been reported by tenant and not yet inspected | Routine repair | Complete | 2024-03-27 |  | 2024-04-16 | 20 | 2024-04-02 | 6 | 2024-05-09 | 37 | 2024-03-27 | 0 | 1 | 2024-04-02 | 2024-02-04 | 0 | 0
61192 | Customer has locked back door but is unable to unlock | Routine repair | Complete | 2024-03-27 |  | 2024-04-16 | 20 | 2024-04-02 | 6 | 2024-05-09 | 37 | 2024-03-27 | 0 | 1 | 2024-04-02 | 2024-02-04 | 0 | 0
61136 | *Mould has been reported by tenant and not yet inspected | Routine repair | Complete | 2024-03-25 |  | 2024-04-14 | 20 | 2024-06-14 | 81 | 2024-07-18 | 34 | 2024-03-26 | 1 | 2 | 2024-03-26 | 2024-03-26 | 0 | 0
61069 | Quote For Replacement of Patio doors (Images will be forwarded) | Routine repair | Complete | 2024-03-21 |  | 2024-04-10 | 20 | 2024-04-03 | 13 | 2024-05-24 | 51 | 2024-03-27 | 6 | 1 | 2024-04-03 | 2024-04-03 | 0 | 0
61065 | Please attend to resolve issues with the extractor fan | Routine repair | Complete | 2024-03-21 |  | 2024-04-10 | 20 | 2024-03-26 | 5 | 2024-07-18 | 114 | 2024-03-21 | 0 | 1 | 2024-03-26 | 2024-03-25 | 0 | 0
61050 | Please attend asap to resolve issues with the plug socket | Routine repair | Complete | 2024-03-21 |  | 2024-04-09 | 20 | 2024-03-26 | 5 | 2024-05-15 | 50 | 2024-03-26 | 5 | 1 | 2024-03-26 | 2024-03-26 | 0 | 0
61006 | *Mould has been reported by tenant and not yet inspected | Routine repair | Complete | 2024-03-19 |  | 2024-04-08 | 20 | 2024-03-22 | 3 | 2024-05-07 | 46 | 2024-03-21 | 2 | 1 | 2024-03-22 | 2024-03-22 | 0 | 0
60957 | Roof tiles loose or broken | Routine repair | Complete | 2024-03-18 |  | 2024-04-07 | 20 | 2024-03-20 | 2 | 2024-06-20 | 92 | 2024-03-19 | 1 | 1 | 2024-03-20 | 2023-03-19 | 0 | 0
60955 | Drafty door | Routine repair | Complete | 2024-03-18 |  | 2024-04-04 | 20 | 2024-03-26 | 8 | 2024-05-15 | 50 | 2024-03-19 | 1 | 1 | 2024-03-26 | 2024-03-26 | 0 | 0
60954 | Window locks | Routine repair | Complete | 2024-03-18 |  | 2024-04-07 | 20 | 2024-03-26 | 8 | 2024-05-15 | 50 | 2024-03-19 | 1 | 1 | 2024-03-26 | 2025-03-26 | 0 | 0
60803 | Stiff door lock | Emergency repair | Complete | 2024-03-13 |  | 2024-03-14 | 1 | 2024-03-14 | 1 | 2024-05-10 | 57 | 2024-03-13 | 0 | 1 | 2024-03-14 | 2024-03-14 | 0 | 0
60770 | Damp and Mould | Routine repair | Complete | 2024-03-12 |  | 2024-03-31 | 20 | 2024-03-13 | 1 | 2024-05-10 | 58 | 2024-03-12 | 0 | 1 | 2024-03-13 | 2024-03-13 | 0 | 0
60450 | Electrics tripping / Plumbing Issues | Emergency repair | Complete | 2024-03-11 |  | 2024-03-12 | 1 | 2024-03-12 | 1 | 2024-07-04 | 114 | 2024-03-11 | 0 | 2 | 2024-03-11 | 2024-03-11 | 0 | 0
60432 | En Suite Shower | Routine repair | Complete | 2024-03-08 |  | 2024-03-28 | 20 | 2024-03-11 | 3 | 2024-05-10 | 60 | 2024-03-08 | 0 | 1 | 2024-03-11 | 2024-03-11 | 0 | 0
60421 | Overhaul Door | Routine repair | Complete | 2024-03-08 |  | 2024-03-28 | 20 | 2024-03-13 | 5 | 2024-05-10 | 58 | 2024-03-08 | 0 | 1 | 2024-03-13 | 2024-03-13 | 0 | 0
60416 | Bedroom -have no sealant around the window frame( PVCu beads ) The windowsill is falling down | Emergency repair | Complete | 2024-03-07 |  | 2024-03-08 | 1 | 2024-03-08 | 1 | 2024-05-10 | 63 | 2024-03-07 | 0 | 1 | 2024-03-08 | 2024-03-08 | 0 | 0
60414 | Damp stain in Bathroom | Routine repair | Complete | 2024-03-07 |  | 2024-03-27 | 20 | 2024-03-08 | 1 | 2024-05-10 | 63 | 2024-03-07 | 0 | 1 | 2024-03-08 | 2024-03-08 | 0 | 0
60383 | Renew Mortice Deadlock | Routine repair | Complete | 2024-03-06 |  | 2024-03-26 | 20 | 2024-03-07 | 1 | 2024-05-07 | 61 | 2024-03-06 | 0 | 1 | 2024-03-07 | 2024-03-07 | 0 | 0
60365 | Front door lock is not working, customer is locked out | Emergency repair | Complete | 2024-03-06 |  | 2024-03-07 | 1 | 2024-03-07 | 1 | 2024-05-10 | 64 | 2024-03-07 | 1 | 1 | 2024-03-07 |  | 0 | 0
60300 | Tenant has mould and damp in the bathroom by the | Routine repair | Complete | 2024-02-28 |  | 2024-03-19 | 20 | 2024-03-04 | 5 | 2024-05-10 | 67 | 2024-02-29 | 1 | 1 | 2024-03-04 | 2024-03-04 | 0 | 0
59994 | - Customers front door wasn't sealed | Routine repair | Complete | 2024-02-13 |  | 2024-03-04 | 20 | 2024-02-14 | 1 | 2024-05-10 | 86 | 2024-02-14 | 1 | 1 | 2024-02-14 | 2024-03-14 | 0 | 0
59993 | Emergency Carpentry and Joinery Repairs and Maintenance | Emergency repair | Complete | 2024-02-13 |  | 2024-02-14 | 1 | 2024-03-25 | 41 | 2024-05-07 | 43 | 2024-02-13 | 0 | 3 | 2024-02-15 | 2024-02-15 | 0 | 0
59991 | Lockable post box | Routine repair | Complete | 2024-02-13 |  | 2024-03-04 | 20 | 2024-02-13 | 0 | 2024-05-10 | 87 | 2024-02-13 | 0 | 1 | 2024-02-13 |  | 0 | 0
59980 | renew lead cover flashing over 300mm and ne 450mm girth. clean out groove of brickwork, wedge | Routine repair | No charge | 2024-02-12 |  | 2024-03-03 | 20 | 2024-11-12 | 274 |  |  | 2024-02-14 | 2 | 2 | 2024-02-15 | 2024-02-15 | 0 | 0
59882 | Damp, Mould & Condensation | Routine repair | Complete | 2024-02-07 |  | 2024-02-27 | 20 | 2024-02-15 | 8 | 2024-05-10 | 85 | 2024-02-07 | 0 | 1 | 2024-02-15 | 2024-02-15 | 0 | 0